## Tasks
Composition | Component | Feature | Reuse Rate | Responsible | Effort Estimate(ITK part)/(HC*Month)
SW Architecture | Architecture design & Doc |  | 50% | ITK, WF, XC | 8
Fundamental | Jenkins | Jenkins | 75% | ITK | 2
| Environment Setup | folder stcuct | 75% | ITK | 2
build Environment
gtest environment
RTA-CAR Tool config - create sw-link to arxml - fix BSW/OS confilict
OS and BSW generate codes problem
scons optimize (seprate coem from PF)
support folder/file variant
| Flash layout | Flash layout definition | 50% | ITK | 2
rbBlock definiton and implemenation
rbBlock adaption
rbBlock generated tool (python)
The block detail of data(WFDA/CLDA/CUDA)
The block detail of exe (Boot, App, Hsm)
Load CUDA/BODA/... to RAM and keep the varianbles
| RAM layout | RAM layout design and ld implemenation | 50% | ITK | 1
Test performance
| Variant handling | Customer build variant | 75% | ITK | 0.5
KL15/KL30 variant
develop/series/ETHDAQ build variant (ETH, others)
Com | Can com Stack | CAN driver mailbox | 50% | ITK | 2
Dynamic RX CanId implementation
SGU/TGU TX
PubCAN from COEM
Signal mapping
E2E, timeout monitoring
Signal valid monitoring
Com Ipdu Group switch ON/OFF for $28
| ETH Com Stack | TI ETH driver
TI ETH driver test and merge to master
ETAS deliver TCPIP cluster
wrap interface for ASW
PIN dection from NvM
ASW adaption
build variant for AWR2E44LC and AWR2E44P
| NM | CAN driver mailbox | 50% | ITK | 1
CanIf, CanNm implementation
Adaption for KL15/KL30
| Time Sync | CanTsync（PF+Customer）
StbM（PF+Customer）
Be able to config to master or slave
| CanSm | MCAL API | 50% | ITK | 1
CanSm & busoff monitoring
FM | Fault Management | BFM(记录ITC详细信息) additional debug infor | 50% | ITK | 2
Event Mask（屏蔽DTC,ITC）
Fault event handling（EVM , up to 10 items
PF enable/storage condition
failure clusters handling（FIM降级相关处理）
supply voltage monioring
PF snapshot/extended data in Bosch session
Customer snapshot/extended data
Add customer event/fault for all module
Add PF event/fault for all module
Dem_GetDtcStatuesBit0(DtcId) API
PF监控降级表以及自动化
Diag | Diagnostic | $10 session control (ISO14229) | 50% | ITK | 2
$10 bosch session requirement docu
$10 session control (bosch session, 10 60)
$11 reset control (11 01/03)
$27 PF(bosch session) security access
$31 calibration（EOL/SDA）
$22 PF DID
$2E PF DID
$28 communicaiton control
85
$14, 19
FBL interaction
NvM | Memory stack | fls driver and MemIf | 50% | ITK | 2
NvM configuration
NvM Interface examle
rbSecFls data
EDR support to ASW
rbService | rbMpr Mounting Pin Recigtion | APP PIN detection DDD (from HW to Service) | 75% | ITK | 1.5
APP MCAL implementation
APP Service Implmentation
FBL rbMpr
| rbTime | rbTime which provide ECU local time - ignition counter - GetEcuLocalTimeMs - GetEcuLocalTimeUs - GetMostAccuate()
| rbVhm Variant handing Manager | DDD | 50% | ITK | 1
Implementation
XCP | XCP | XCP demo test | 50% | ITK | 2
定义方案
定义观测量和标定量
为表定量分配RAM和Flash区域
CANape工具配置
A2L文件生成
RTE | RTE |  | 50% | ITK | 2
ASW | ASW/ITK part |  | 25% | ITK | 3
| ASW/WF part |  | NA | WF
OS | Task, ISR | mmwave block BSW_10ms 200ms problem | 50% | ITK | 2
task 调度 & 优先级设计
ISR中断处理
CPU usage, 执行时间，周期统计
task 超时监控
stack配置和监控
runtime report from XCP & MF4
MCAL & CDD | MCAL | GPT driver | 50% | ITK | 2
Can Driver
SPI driver
Fls driver
IPC driver
ETH driver
Adc driver
DIO driver
Port driver
| PMIC & Watchdog | Watchdog driver | 25%/75% | ITK | 1
Put watchdog protection to task
PMIC driver
PMIC error handler
| CDD | CAN transciver driver | 25%/75% | ITK | 0.5
ETH transciver driver
LCM | startup/shutdown | startup/shutdown | 50% | ITK | 4
| 睡眠/唤醒 | 睡眠/唤醒
| HW monitoring(Memory, Register Acess, Clock, FPU, Stack, Task Alive check, Lockstep, Static Config...) | HW monitoring(Memory, Register Acess, Clock, FPU, Stack, Task Alive check, Lockstep, Static Config...)
| 温度监控，供电电压监控 | 温度监控，供电电压监控
| exception handling | exception handling
| Save error log to NvM | Save error log to NvM
DSP&HWA | DSP&HWA | DSP&HWA | NA | WF
RF | mmWave Link | 1. dpu | NA | WF
2. dpc
3. dpcedma
4. dpif
5. esm
| MW | 1. 核内IPC | NA | WF
2. 核间IPC
3. cache enable & 一致性
4. 胶水代码自动工具生成
5. 错误信息检查&记录
| RF Diagnosis |  | 50% | ITK | 2
Boot | BootManager | MiniBoot: Jump to FBL once receive a CAN special signal | 75% | ITK | 1.5
MiniBoot: Securrify boot
MiniBoot: Load WfBoot/FBL test
MiniBoot: rbBlock adaption
| WfBoot | WfBoot: 刷写CRC校验 | 75% | ITK | 1.5
WfBoot: $27服务
WfBoot: Support dump NvM
WfBoot: 安全刷写
WfBoot: rbBlock adaption
| CustBoot | CustBoot：实现客户需求 | 50% | ITK | 3
CustBoot 刷写CRC校验
CustBoott: rbBlock adaption
CustBoot: 安全刷写
Seurity | CycurSoC integrate | VMS Step2(key and certificate) | 75% | ITK | 2
host driver
| HW interface Protection | JTAG Protection | 75% | ITK | 0.5
| Secure boot | TI defined boot header(HSM/SBL) genenration | 50% | ITK | 1
HSM runtime boot (SBL verify HSM, code implementation)
block structure construct(encrypt/sign/CRC)
APP SW block boot (逐级验证)
| Efuse key writter | efuse for development use | 75% | ITK | 0.5
support plant
| signing tool adaption | for secure flashing, secure boot, key writter | 50% | ITK | 1
| secure flashing | deliver requirement to FBL (FBL support) | 50% | ITK | 2
| RB Secure access |  | 75% | ITK | 0.5
| Secure lifecycle | secure lifecycle based on API provided by ETAS | 75% | ITK | 0.5
UART protection
| Secure storage | NVM design support | 75% | ITK | 0.5
provision and update key
| customer secure accesss |  | 50% | ITK | 1
| KMS ( The cost is't included.) |  | 0% | ITK
Safety | System |  | 0% | ITK | 21
| Hardware(FMEDA) |  | 0% | ITK | 3
| Software | BIST: PBIST, LBIST, MBIST | 0% | ITK | 35
Monitor: Register, Voltage, Clock
Mem Test: RAM, ROM
ESM
Watch Dog: Internal, External
Watch Dog: Alive Monitor
Watch Dog: Program Flow Monitor
Watch Dog:Deadline Monitor
OS: MPU
OS Hook: error hook, protection hook
PMIC: Voltage monitor
PMIC: Temp monitor
PMIC: ErrPin
PMIC: Shutoff path
Analog/RF and Digital Monitor
Tools | Tools | COM, FM 自动化代码脚本 | 75% | WF | 3
|  | 数据录取工具 |  | WF
|  | 仿真工具 |  | WF
|  | 诊断工具(ADM) |  | ITK
|  | 通信工具（restbus） |  | ITK
|  | 软件刷写工具(xflash) |  | ITK
|  | NVM 解析工具(PDV) |  | ITK
|  | runtime分析工具 |  | ITK
|  | 资源使用分析工具（RAM/ROM/NVM） |  | ITK
PV | PV requirements development/WF Part |  | NA | WF
| PV requirements development/ITK Part |  | 50% | ITK | 3
| PV variant management |  |  | ITK
DV | DV requirements development/WF Part |  | NA | WF
| DV requirements development/ITK Part |  | 50% | ITK | 3
| PV variant management |  |  | ITK
EOL | EOL requirements development/WF Part |  | NA | WF
| EOL requirements development/ITK Part |  | 50% | ITK | 5
| EOL Tools |  |  | ITK
| EOL variant management |  |  | ITK
Integration&CICT | Integration&CICT |  | 0% | ITK | 14
SW Test | SW Test |  | 0% | ITK | 21
Project Management | Project Management |  | 0% | ITK | 7
QA | Quality Assurance |  | 0% | ITK | 3.5
|  |  |  | Sum | 180.5
Note 1. Reuse Rate 0%: New development; 25%: Minor reuse, similar to CanTrcv replacement; 50%: Partial reuse, similar to development customer Spec; 75%: Majority reuse, with only minor adaptations and verification required; 100%: Direct reuse.